## Scope of Work Timeline
Version: April 22, 2009
Community Behavioral Health Organization |  |  |  | Pilot |  |  | Training |  | Evaluation |  | Final Implementation
Foundation for the Future Change Initiative
Implemenation Scope of Work and Timeline |  | 2009 | [9 empty] | 2010 | [11 empty] | 2011
Scope of Work Tasks |  | 2009-05-06 | 2009-06-06 |  | 2009-07-06 | 2009-08-06 |  | 2009-09-06 | 2009-10-06 | 2009-11-06 | 2009-12-06 | 2010-01-06 | 2010-02-06 | 2010-03-06 | 2010-04-06 | 2010-05-06 | 2010-06-06 | 2010-07-06 | 2010-08-06 | 2010-09-06 | 2010-10-06 | 2010-11-06 | 2010-12-06 | 2011-01-06
CSIT 1 | Develop New Organizational Models/ Structures to support a Fully Integrated Service Delivery System including a centralized intake process.
1
►
►
►
►
►
►
2
►
►
►
►
►
►
►
►
►
3
►
►
►
►
►
►
►
Develop Core Competency training plan to ensure staff readiness for new service delivery and organizational model(s)
4
►
►
►
►
►
►
►

## Central Intake Phase A Tasks
► Back to Timeline
Implementation Project Manager:
(Step by Step Analysis)
Tools
Manuals: | Responsible Person | Task | Start Date | Due Date | Decision Status
Methods/Procedures: | Responsible Person | Task | Start Date | Due Date | Decision Status
a. Skills Assessment
b. Pilots
c. Proof of Concepts
Technology: | Responsible Person | Task | Start Date | Due Date | Decision Status
Resources/Materials: | Responsible Person | Task | Start Date | Due Date | Decision Status
Training Events: | Responsible Person | Task | Start Date | Due Date | Decision Status
Communications: | Responsible Person | Task | Start Date | Due Date | Decision Status

## Central Intake Phase B Tasks
► Back to Timeline
Implementation Project Manager:
(Step by Step Analysis)
Tools
Manuals: | Responsible Person | Task | Start Date | Due Date | Decision Status
Methods/Procedures: | Responsible Person | Task | Start Date | Due Date | Decision Status
a. Skills Assessment
b. Pilots
c. Proof of Concepts
Technology: | Responsible Person | Task | Start Date | Due Date | Decision Status
Resources/Materials: | Responsible Person | Task | Start Date | Due Date | Decision Status
Training Events: | Responsible Person | Task | Start Date | Due Date | Decision Status
Communications: | Responsible Person | Task | Start Date | Due Date | Decision Status

## Central Intake "B" Evaluation
► Back to Timeline
Implementationm Project Manager:
(Step by Step Analysis)
Tools
Manuals: | Responsible Person | Task | Start Date | Due Date | Decision Status
Methods/Procedures: | Responsible Person | Task | Start Date | Due Date | Decision Status
a. Skills Assessment
b. Pilots
c. Proof of Concepts
Technology: | Responsible Person | Task | Start Date | Due Date | Decision Status
Resources/Materials: | Responsible Person | Task | Start Date | Due Date | Decision Status
Training Events: | Responsible Person | Task | Start Date | Due Date | Decision Status
Communications: | Responsible Person | Task | Start Date | Due Date | Decision Status

## Central Intake Phase C Tasks
| Central Intake Phase C Task List: |  |  | ► Back to Timeline
Implementation Project Manager:
(Step by Step Analysis)
Tools
Manuals: | Responsible Person | Task | Start Date | Due Date | Decision Status
Methods/Procedures: | Responsible Person | Task | Start Date | Due Date | Decision Status
a. Skills Assessment
b. Pilots
c. Proof of Concepts
Technology: | Responsible Person | Task | Start Date | Due Date | Decision Status
Resources/Materials: | Responsible Person | Task | Start Date | Due Date | Decision Status
Training Events: | Responsible Person | Task | Start Date | Due Date | Decision Status
Communications: | Responsible Person | Task | Start Date | Due Date | Decision Status

## Central Intake "C" Evaluation
| Central Intake Phase C Evaluation Task List: |  |  | ► Back to Timeline
Implementation Project Manager:
(Step by Step Analysis)
Tools
Manuals: | Responsible Person | Task | Start Date | Due Date | Decision Status
Methods/Procedures: | Responsible Person | Task | Start Date | Due Date | Decision Status
a. Skills Assessment
b. Pilots
c. Proof of Concepts
Technology: | Responsible Person | Task | Start Date | Due Date | Decision Status
Resources/Materials: | Responsible Person | Task | Start Date | Due Date | Decision Status
Training Events: | Responsible Person | Task | Start Date | Due Date | Decision Status
Communications: | Responsible Person | Task | Start Date | Due Date | Decision Status

## Central Intake Final Implement
| Central Intake Final Implementation Task List: |  |  | ► Back to Timeline
Implementation Project Manager:
(Step by Step Analysis)
Tools
Manuals: | Responsible Person | Task | Start Date | Due Date | Decision Status
Methods/Procedures: | Responsible Person | Task | Start Date | Due Date | Decision Status
a. Skills Assessment
b. Pilots
c. Proof of Concepts
Technology: | Responsible Person | Task | Start Date | Due Date | Decision Status
Resources/Materials: | Responsible Person | Task | Start Date | Due Date | Decision Status
Training Events: | Responsible Person | Task | Start Date | Due Date | Decision Status
Communications: | Responsible Person | Task | Start Date | Due Date | Decision Status

## Client Scheduling Phase A
| Client Scheduling Phase A No Show Task List: |  |  | ► Back to Timeline
Implementation Project Manager:
(Step by Step Analysis)
Tools
Manuals: | Responsible Person | Task | Start Date | Due Date | Decision Status
Methods/Procedures: | Responsible Person | Task | Start Date | Due Date | Decision Status
a. Skills Assessment
b. Pilots
c. Proof of Concepts
Technology: | Responsible Person | Task | Start Date | Due Date | Decision Status
Resources/Materials: | Responsible Person | Task | Start Date | Due Date | Decision Status
Training Events: | Responsible Person | Task | Start Date | Due Date | Decision Status
Communications: | Responsible Person | Task | Start Date | Due Date | Decision Status

## Review Revise No Show Procdures
Client Scheduling Review/Revise No Show Procedures Task List: |  |  |  | ► Back to Timeline
Implementation Project Manager:
(Step by Step Analysis)
Tools
Manuals: | Responsible Person | Task | Start Date | Due Date | Decision Status
(11/1/06)
Methods/Procedures: | Responsible Person | Task | Start Date | Due Date | Decision Status
a. Skills Assessment
b. Pilots
c. Proof of Concepts
Technology: | Responsible Person | Task | Start Date | Due Date | Decision Status
Resources/Materials: | Responsible Person | Task | Start Date | Due Date | Decision Status
Training Events: | Responsible Person | Task | Start Date | Due Date | Decision Status
Communications: | Responsible Person | Task | Start Date | Due Date | Decision Status

## Train Staff No Show Procedures
Client Scheduling Initial No Show Staff Training Task List: |  |  |  | ► Back to Timeline
Implementation Project Manager:
(Step by Step Analysis)
Tools
Manuals: | Responsible Person | Task | Start Date | Due Date | Decision Status
Methods/Procedures: | Responsible Person | Task | Start Date | Due Date | Decision Status
a. Skills Assessment
b. Pilots
c. Proof of Concepts
Technology: | Responsible Person | Task | Start Date | Due Date | Decision Status
Resources/Materials: | Responsible Person | Task | Start Date | Due Date | Decision Status
Training Events: | Responsible Person | Task | Start Date | Due Date | Decision Status
Communications: | Responsible Person | Task | Start Date | Due Date | Decision Status

## First No Show Implementation
Client Scheduling First No Show Implementation Task List: |  |  |  | ► Back to Timeline
Implementation Project Manager:
(Step by Step Analysis)
Tools
Manuals: | Responsible Person | Task | Start Date | Due Date | Decision Status
Methods/Procedures: | Responsible Person | Task | Start Date | Due Date | Decision Status
a. Skills Assessment
b. Pilots
c. Proof of Concepts
Technology: | Responsible Person | Task | Start Date | Due Date | Decision Status
Resources/Materials: | Responsible Person | Task | Start Date | Due Date | Decision Status
Training Events: | Responsible Person | Task | Start Date | Due Date | Decision Status
Communications: | Responsible Person | Task | Start Date | Due Date | Decision Status

## No Show Training Remainder
Client Scheduling No Show Training Remainder of Staff Task List: |  |  |  | ► Back to Timeline
Implementation Project Manager:
(Step by Step Analysis)
Tools
Manuals: | Responsible Person | Task | Start Date | Due Date | Decision Status
(11/1/06)
Methods/Procedures: | Responsible Person | Task | Start Date | Due Date | Decision Status
a. Skills Assessment
b. Pilots
c. Proof of Concepts
Technology: | Responsible Person | Task | Start Date | Due Date | Decision Status
Resources/Materials: | Responsible Person | Task | Start Date | Due Date | Decision Status
Training Events: | Responsible Person | Task | Start Date | Due Date | Decision Status
Communications: | Responsible Person | Task | Start Date | Due Date | Decision Status

## Final Implementation of No Show
Client Scheduling Final No Show Implementation Task List: |  |  |  | ► Back to Timeline
Implementation Project Manager:
(Step by Step Analysis)
Tools
Manuals: | Responsible Person | Task | Start Date | Due Date | Decision Status
(11/1/06)
Methods/Procedures: | Responsible Person | Task | Start Date | Due Date | Decision Status
a. Skills Assessment
b. Pilots
c. Proof of Concepts
Technology: | Responsible Person | Task | Start Date | Due Date | Decision Status
Resources/Materials: | Responsible Person | Task | Start Date | Due Date | Decision Status
Training Events: | Responsible Person | Task | Start Date | Due Date | Decision Status
Communications: | Responsible Person | Task | Start Date | Due Date | Decision Status

## Client Scheduling Phase B
| Client Scheduling Phase B Task List: |  |  | ► Back to Timeline
Implementation Project Manager:
(Step by Step Analysis)
Tools
Manuals: | Responsible Person | Task | Start Date | Due Date | Decision Status
Methods/Proedures: | Responsible Person | Task | Start Date | Due Date | Decision Status
a. Skills Assessment
b. Pilots
c. Proof of Concepts
Technology: | Responsible Person | Task | Start Date | Due Date | Decision Status
Resources/Materials: | Responsible Person | Task | Start Date | Due Date | Decision Status
Training Events: | Responsible Person | Task | Start Date | Due Date | Decision Status
Communications: | Responsible Person | Task | Start Date | Due Date | Decision Status

## Central Scheduling Eval Phase B
| Client Scheduling Phase B Evaluation Task List: |  |  | ► Back to Timeline
Implementation Project Manager:
(Step by Step Analysis)
Tools
Manuals: | Responsible Person | Task | Start Date | Due Date | Decision Status
(11/1/06)
Methods/Procedures: | Responsible Person | Task | Start Date | Due Date | Decision Status
a. Skills Assessment
b. Pilots
c. Proof of Concepts
Technology: | Responsible Person | Task | Start Date | Due Date | Decision Status
Resources/Materials: | Responsible Person | Task | Start Date | Due Date | Decision Status
Training Events: | Responsible Person | Task | Start Date | Due Date | Decision Status
Communications: | Responsible Person | Task | Start Date | Due Date | Decision Status

## Central Schedule Final Implemen
| Client Scheduling Final Implementation Task List: |  |  | ► Back to Timeline
Implementation Project Manager:
(Step by Step Analysis)
Tools
Manuals: | Responsible Person | Task | Start Date | Due Date | Decision Status
(11/1/06)
Methods/Procedures: | Responsible Person | Task | Start Date | Due Date | Decision Status
a. Skills Assessment
b. Pilots
c. Proof of Concepts
Technology: | Responsible Person | Task | Start Date | Due Date | Decision Status
Resources/Materials: | Responsible Person | Task | Start Date | Due Date | Decision Status
Training Events: | Responsible Person | Task | Start Date | Due Date | Decision Status
Communications: | Responsible Person | Task | Start Date | Due Date | Decision Status

## Front Desk Phase A Check In-Out
Front Desk Phase A Pilot - Check In/Out and Benefiting Task List: |  |  |  | ► Back to Timeline
Implementation Project Manager:
(Step by Step Analysis)
Tools
Manuals: | Responsible Person | Task | Start Date | Due Date | Decision Status
Methods/Procedures: | Responsible Person | Task | Start Date | Due Date | Decision Status
a. Skills Assessment
b. Pilots
c. Proof of Concepts
Technology: | Responsible Person | Task | Start Date | Due Date | Decision Status
Resources/Materials: | Responsible Person | Task | Start Date | Due Date | Decision Status
Training Events: | Responsible Person | Task | Start Date | Due Date | Decision Status
Communications: | Responsible Person | Task | Start Date | Due Date | Decision Status

## Front Desk Evaluation Phase A
Front Desk Phase A Pilot Check In/Out and Benefiting Evaluation Task List: |  |  |  | ► Back to Timeline
Implementation Project Manager:
(Step by Step Analysis)
Tools
Manuals: | Responsible Person | Task | Start Date | Due Date | Decision Status
(11/1/06)
Methods/Procedures: | Responsible Person | Task | Start Date | Due Date | Decision Status
a. Skills Assessment
b. Pilots
c. Proof of Concepts
Technology: | Responsible Person | Task | Start Date | Due Date | Decision Status
Resources/Materials: | Responsible Person | Task | Start Date | Due Date | Decision Status
Training Events: | Responsible Person | Task | Start Date | Due Date | Decision Status
Communications: | Responsible Person | Task | Start Date | Due Date | Decision Status

## Front Desk Train Staff
Front Desk Staff Check In/Out and Benefiting Training Task List: |  |  |  | ► Back to Timeline
Implementation Project Manager:
(Step by Step Analysis)
Tools
Manuals: | Responsible Person | Task | Start Date | Due Date | Decision Status
Methods/Procedures: | Responsible Person | Task | Start Date | Due Date | Decision Status
a. Skills Assessment
b. Pilots
c. Proof of Concepts
Technology: | Responsible Person | Task | Start Date | Due Date | Decision Status
Resources/Materials: | Responsible Person | Task | Start Date | Due Date | Decision Status
Training Events: | Responsible Person | Task | Start Date | Due Date | Decision Status
Communications: | Responsible Person | Task | Start Date | Due Date | Decision Status

## Front Desk Phased Implement
Front Desk Phased Check In/Out and Benefiting Implementation Task List: |  |  |  | ► Back to Timeline
Implementation Project Manager:
(Step by Step Analysis)
Tools
Manuals: | Responsible Person | Task | Start Date | Due Date | Decision Status
Methods/Procedures: | Responsible Person | Task | Start Date | Due Date | Decision Status
a. Skills Assessment
b. Pilots
c. Proof of Concepts
Technology: | Responsible Person | Task | Start Date | Due Date | Decision Status
Resources/Materials: | Responsible Person | Task | Start Date | Due Date | Decision Status
Training Events: | Responsible Person | Task | Start Date | Due Date | Decision Status
Communications: | Responsible Person | Task | Start Date | Due Date | Decision Status

## Front Desk Phase B Pilot
Front Desk Phase B Client Scheduling Pilot Task List: |  |  |  | ► Back to Timeline
Implementation Project Manager:
(Step by Step Analysis)
Tools
Manuals: | Responsible Person | Task | Start Date | Due Date | Decision Status
Methods/Procedures: | Responsible Person | Task | Start Date | Due Date | Decision Status
a. Skills Assessment
b. Pilots
c. Proof of Concepts
Technology: | Responsible Person | Task | Start Date | Due Date | Decision Status
Resources/Materials: | Responsible Person | Task | Start Date | Due Date | Decision Status
Training Events: | Responsible Person | Task | Start Date | Due Date | Decision Status
Communications: | Responsible Person | Task | Start Date | Due Date | Decision Status

## Front Desk Phase B Eval
Front Desk Phase B Client Scheduling Evaluation Task List: |  |  |  | ► Back to Timeline
Implementation Project Manager:
(Step by Step Analysis)
Tools
Manuals: | Responsible Person | Task | Start Date | Due Date | Decision Status
Methods/Procedures: | Responsible Person | Task | Start Date | Due Date | Decision Status
a. Skills Assessment
b. Pilots
c. Proof of Concepts
Technology: | Responsible Person | Task | Start Date | Due Date | Decision Status
Resources/Materials: | Responsible Person | Task | Start Date | Due Date | Decision Status
Training Events: | Responsible Person | Task | Start Date | Due Date | Decision Status
Communications: | Responsible Person | Task | Start Date | Due Date | Decision Status

## Front Desk Final Implementation
Front Desk Final Implementation Task List: |  |  |  | ► Back to Timeline
Implementation Project Manager:
(Step by Step Analysis)
Tools
Manuals: | Responsible Person | Task | Start Date | Due Date | Decision Status
Methods/Procedures: | Responsible Person | Task | Start Date | Due Date | Decision Status
a. Skills Assessment
b. Pilots
c. Proof of Concepts
Technology: | Responsible Person | Task | Start Date | Due Date | Decision Status
Resources/Materials: | Responsible Person | Task | Start Date | Due Date | Decision Status
Training Events: | Responsible Person | Task | Start Date | Due Date | Decision Status
Communications: | Responsible Person | Task | Start Date | Due Date | Decision Status